## Progress Report
BTG Grade Submission System
Weekly Progress Report
July 5-11, 2016
Project Details
Project Name | BTG Grade Submission System | Project Coordinator | Erwin Sarmiento
Start Date | 2016-07-05 | Project Leader | Christian Dave B. Baclayon
End Date | 2016-07-11 | Project Members | Adrian P. Rivera
James Russell A. Codilla
Joannah Rabilas
Project Status
Recent Milestone Deliverable | Project Proposal
On-going Milestone Deliverable | Project Plan
Schedule | OK
Cost | OK
People | OK
Accomplishments for the Week
Task | Target % | Actual Completion % | Comments
Project Proposal | 100% | 100%
Project Plan | 50% | 100%
June Meeting Minutes | 100% | 100%
| 100% | 100%
| 100% | 100%
| 100% | 100%
| 100% | 100%
| 100% | 100%
| 100% | 100%
| 100% | 100%
| 100% | 100%
| 100% | 100%
| 100% | 100%
| 100% | 100%
Percentage Status Reporting
Documentation Tasks/Coding/Testing |  | Study/Training/Research/Investigation/Installation/Setup
*Started | 10%
*Completed | 30% | Progress Percentage = (Used up Number of hours / Allocated Number of hours) x 100%
*Reviewed | 50%
*Updated | 80%
*Confirmed/Approved | 100%
Tasks for Next Week
Task | Target % | Actual Completion % | Comments
Requirements Analysis for Class Management | 10% | 0%
Requirements Analysis for Teacher Management | 10% | 0%
Requirements Analysis for Subject Management | 10% | 0%
Requirements Analysis for Track Management | 10% | 0%
Requirements Analysis for Grades Management | 10% | 0%
| 10% | 0%
| 10% | 0%
| 10% | 0%
| 10% | 0%
| 10% | 0%
| 10% | 0%
| 10% | 0%
Project Data
SDLC Stage | Estimated Value | Actual Value | Comments
Project Cost | P0000.00 | P0000.00
Project Planning Effort | 0.5 mm/pax | 2.5 mm
Requirements Dev't Effort | 1 mm/pax | 5 mm
Design Effort | 2 mm/pax | 10 mm
Coding Effort | 3 mm/pax | 15 mm
Unit Testing Effort | 1 mm/pax | 5 mm
Integration Testing Effort | 1 mm/pax | 5 mm
System Testing Effort | N/A | N/A
Note on C14: Erwin Sarmiento: Deliverable that is already approved after team revision based on review by Project Coordinator.
Note on C15: Erwin Sarmiento: Deliverable that is already approved after team revision based on review by Project Coordinator.
Note on D16: Erwin Sarmiento: If NG, always specify reason and contigency or back up plan.
Note on F16: Erwin Sarmiento:
Note on E20: Abalquin: If delayed, place comments.
Note on F60: Erwin Sarmiento: Actual value is Estimated Value times the number of people in the team plus Project Coordinator. Actual Value unit of measurement is mm only.

## Appendix
Milestone Deliverables | Tasks
Project Proposal | Project Proposal
Project Plan | Project Plan
Requirements Specification | Requirements Analysis for Class Management
Screen Definition | Requirements Analysis for Teacher Management
Database Design | Requirements Analysis for Subject Management
Class Diagram | Requirements Analysis for Track Management
Sequence Diagram | Requirements Analysis for Grades Management
Software Architecture | Screen Definition for Class Management
Coding Guidelines | Screen Definition for Teacher Management
Source Codes | Screen Definition for Subject Management
Internal Release 1 | Screen Definition for Track Management
Internal Release 2 | Screen Definition for Grades Mangement
Internal Release 3 | Class Diagram
Unit Test Specifications | Database Design
Unit Test Results | Software Architecture
Integration Test Specifications | Sequence Diagram for Class Management
Integration Test Results | Sequence Diagram for Teacher Management
Alpha Release | Sequence Diagram for Subject Management
Beta Release | Sequence Diagram for Track Management
Gamma Release | Sequence Diagram for Grades Management
Project Completion Report | Conding Guidelines
Implementation of Class Management
Implementation of Teacher Management
Implementation of Subject Management
Implementation of Track Management
Implementation of Grades Management
Unit Test Specification for Class Management
Unit Test Specification for Teacher Management
Unit Test Specification for Subject Management
Unit Test Specification for Track Management
Unit Test Specification for Grades Management
Unit Test Execution for Class Management
Unit Test Execution for Teacher Management
Unit Test Execution for Subject Management
Unit Test Execution for Track Management
Unit Test Execution for Grades Management
Unit Test Bug Fixing for Class Management
Unit Test Bug Fixing for Teacher Management
Unit Test Bug Fixing for Subject Management
Unit Test Bug Fixing for Track Management
Unit Test Bug Fixing for Grades Management
Integration Test Specification for Class Management
Integration Test Specification for Teacher Management
Integration Test Specification for Subject Management
Integration Test Specification for Track Management
Integration Test Specification for Grades Management
Integration Test Execution for Class Management
Integration Test Execution for Teacher Management
Integration Test Execution for Subject Management
Integration Test Execution for Track Management
Integration Test Execution for Grades Management
Integration Test Bug Fixing for Class Management
Integration Test Bug Fixing for Teacher Management
Integration Test Bug Fixing for Subject Management
Integration Test Bug Fixing for Track Management
Integration Test Bug Fixing for Grades Management
Alpha Release
Beta Release
Gamma Release
Project Completion Report